## Agile Project Plan
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
Product Release | Zae Saeed | 2019-03-15 | 2019-05-02 |  | 65% |  | SCOPE STATEMENT
TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1 |  |  |  | 2019-03-16 | 2019-03-31 | 15 | Completed
Feature 1 | Platform Setup | Dylan, Gilbert | 1,2 | 2019-03-16 | 2019-03-23 | 5 | Complete | Set up platforms/environments
Feature 2 | Project Layout | Shahzada S. | 2,3,4 | 2019-03-23 | 2019-03-27 | 5 | Complete | Design/brainstorm project layout
Feature 3 | User Login Form | Jake Loff | 6,7 | 2019-03-27 | 2019-03-31 | 5 | Complete | Start implementation
Sprint 2 |  |  |  | 2019-04-01 | 2019-04-11 | 10 | Completed
Feature 4 | User Creation | Zae S. | 7,8 | 2019-04-01 | 2019-04-04 | 3 | Complete | implement adminstrater features
Feature 5 | User Input Validation | Geo Q. | 9 | 2019-04-04 | 2019-04-07 | 3 | Complete | Implement user features
Feature 6 | Admin. Test Bank Development | Victor C. | 2,3 | 2019-04-07 | 2019-04-11 | 4 | Complete | analysis/testing
Sprint 3 |  |  |  | 2019-04-12 | 2019-04-18 | 6 | Completed
Feature 4 | Database Setup | Shahzada S., Geo Q. | 7,8 | 2019-04-12 | 2019-04-14 | 2 | Complete | implement/ update database
Feature 5 | User Input/ Database Validation | Gilbert A. | 9 | 2019-04-14 | 2019-04-16 | 2 | Complete | Implement/update user features
Feature 6 | File Upload | Victor C. | 2,3 | 2019-04-16 | 2019-04-18 | 2 | Complete | analysis/testing
Sprint 4 |  |  |  | 2019-04-19 | 2019-04-25 | 6 | Complete
Feature 7 | Visual Customization | Dylan D. | 7,8 | 2019-04-19 | 2019-04-24 | 5 | Complete | Edit appearance with UAlbany colors
Feature 8 | User Approval Rating | Gilbert A. | 9 | 2019-04-19 | 2019-04-24 | 5 | Complete | Implement/update user features
Feature 9 | AWS Test | Victor C. | 2,3 | 2019-04-19 | 2019-04-24 | 5 | Complete | Test functionality on AWS cloud
Team Members: Zae Saeed, Dylan Davidson, Gilbert Alvarado, Jacob Loff, Geovanny Quiroz, Shahzada Shah, Victor Compres
Team Members: Zae Saeed, Dylan Davidson, Gilbert Alvarado, Jacob Loff, Geovanny Quiroz, Shahzada Shah, Victor Compres